## Attendant List
Attendant List
No | Name | Start Date | End Date | Course Name | Status | Archivement | Note
1 | Trương Thị Thu Hương | 2019-01-11 | 2019-05-15 | Sierra Wireless Training
2 | Đinh Thị Lưu Uy | 2019-01-11 | 2019-05-15 | Sierra Wireless Training
3 | Phan Thanh Thảo | 2019-01-11 | 2019-05-15 | Sierra Wireless Training
4 | Nguyễn Thị Bích Quy | 2019-01-11 | 2019-05-15 | Sierra Wireless Training
5 | Võ Thị Tú Quyên | 2019-01-11 | 2019-05-15 | Sierra Wireless Training
6 | Bùi Ngọc Can | 2019-01-11 | 2019-05-15 | Sierra Wireless Training
7 | Ung Thị Bích Nga | 2019-01-11 | 2019-05-15 | Sierra Wireless Training

## Sierra Wireless Training Course
Sierra Wireless Training Course From 11/1/2019 To 15/5/2019
No. | Training Outline | Content | Duration (Hours) |  | Objectives | Training Method | Start date | Finish date | Progress | Notes
|  |  | Plan | Actual
Course 1: Sierra Wireless Overview |  |  | 4
1 | Sierra Wireless introduction | Training | 2 |  |  |  | N/A | N/A
2 | Embedded solutions and products | Training | 2 |  |  |  | N/A | N/A
Course 2: Python language Understading |  |  | 36
1 | Python introduction: syntax, variables, loop, array, dates… | Training & Exercise | 4 |  |  |  | 2019-01-11 | 2019-01-11
2 | Python Regular Expression | Training & Exercise | 12 |  |  |  | 2019-01-14 | 2019-01-18
3 | Handle exception in Python | Training & Exercise | 12 |  |  |  | 2019-01-21 | 2019-01-21
4 | File handling | Training & Exercise | 4 |  |  |  | 2019-01-24 | 2019-01-24
After a course | Quiz | Quiz on paper | 1 |  |  |  | N/A | N/A
| Presentation |  | 3 |  |  |  | 2019-01-25 | 2019-01-25
Course 3: Cellular network Understading |  |  | 104
1 | Overview about mobile telecommunication system | Training | 2 |  |  |  | 2019-02-18 | 2019-02-18
2 | 2G cellular network | Training | 2 |  |  |  | 2019-02-18 | 2019-02-18
3 | 3G cellular network | Training | 2 |  |  |  | 2019-02-18 | 2019-02-18
4 | 4G LTE network | Training | 2 |  |  |  | 2019-02-18 | 2019-02-18
5 | 3GPP document introduction | Training | 4 |  |  |  | 2019-02-19 | 2019-02-19
6 | AT command introduction | Training | 4 |  |  |  | 2019-02-19 | 2019-02-19
7 | Practice with AT command | Exercise | 80 |  |  |  | 2019-02-20 | 2019-03-06
After a course | Quiz | Quiz on paper | 4 |  |  |  | 2019-03-07 | 2019-03-07
| Presentation |  | 4 |  |  |  | 2019-03-07 | 2019-03-07
Course 4: Test cases design |  |  | 128
1 | Network Status | Exercise | 24 |  |  |  | 2019-03-08 | 2019-03-12
2 | Call control | Exercise | 24 |  |  |  | 2019-03-13 | 2019-03-15
3 | SMS | Exercise | 24 |  |  |  | 2019-03-18 | 2019-03-20
4 | Frequence | Exercise | 24 |  |  |  | 2019-03-22 | 2019-03-25
5 | General status | Exercise | 24 |  |  |  | 2019-03-26 | 2019-03-28
After a course | Quiz | Quiz on paper | 4 |  |  |  | 2019-03-29 | 2019-03-29
| Presentation |  | 4 |  |  |  | 2019-03-29 | 2019-03-29
Course 5: Scripts Development |  |  | 158
1 | Network Status | Exercise | 30 |  |  |  | 2019-04-01 | 2019-04-05
2 | Call control | Exercise | 30 |  |  |  | 2019-04-07 | 2019-04-12
3 | SMS | Exercise | 30 |  |  |  | 2019-04-15 | 2019-04-19
4 | Frequence | Exercise | 30 |  |  |  | 2019-04-22 | 2019-04-26
5 | General status | Exercise | 30 |  |  |  | 2019-04-29 | 2019-05-03
After a course | Quiz | Quiz on paper | 4 |  |  |  | 2019-05-06 | 2019-05-06
| Presentation |  | 4 |  |  |  | 2019-05-06 | 2019-05-06
Finish course | Capstone Presentation |  | 32 |  |  |  | 2019-05-07 | 2019-05-11
| Backup time |  | 24 |  |  |  | 2019-05-13 | 2019-05-15
Total |  |  | 486
Days |  |  | 60.75
Months |  |  | 3.0375

## POC Project (hidden)
POC Project From 26/3/2019 To 15/5/2019
Purpose:
- Use the knowledge they learned from the course to apply to the actual project.
Method:
- Separate 12 members to 3 groups (4 members / group).
- 3 groups will do a proof of concept for an internal project or a real project from customer.
- Students will be instructed to do POC with Agile software development process and use some project management tools
No | Evaluation method | Description | Evaluator
1 | Everyone in class will cross-assessing each other | Using evaluation form from TIC | Interns
2 | TIC will review, evaluate and give feedbacks each group |  | TIC
3 | Mentor will review and score for each group | Base on TIC evaluation and cross-assessing from students | Mentors
Notes: Passing or failing depends on the research process, the results of quizzes, the results of the POC project, and the most important is working and learning attitude of students

## Budget Plan (hidden)
Budget Plan
No | Expenses | Cost | Note
1 | Salary for 12 members in 4 months | 43200000 | 950,000 VND for each member per month
2 | Reward for the best group in POC project | 1500000 | Evaluated by TIC, mentors and cross-assessing from interns
3 | Reward for the best individual | 500000 | Evaluated by TIC, mentors and cross-assessing from interns
4 | Team building | 4800000 | For some parties during internship course
| Total | 50000000

## Enroll- Course X (hidden)
No | Name | Subject | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Archivement | Note
1 | Nguyễn Van A | #REF! | x | [24 empty] | Create a website with header, title, body, Img tag…

## Sheet1 (hidden)
No | Name | Subject
1 | Nguyễn Van A

## Q&A
No | Question | Answer | Trainer